Instructions For Consulting Firms

For Submission of

EXPRESSION OF INTEREST

HIRING OF A COMMUNICATION FIRM

Housing Reconstruction Unit- Balochistan (HRU) Integrated Flood Resilience and Adaptation Project (IFRAP)

Ministry of Planning, Development & Special Initiatives (MoPD&SI), Government of Pakistan

August, 2025

PART-I

(General Instructions)

- The Housing Reconstruction Unit (HRU-IFRAP) invites eligible consulting firms/ Joint Venture(s) with specific and proven competence and experience to indicate their interest in providing the services. Eligible firm(s) should submit Expression of Interest (EOI) in English language along with relevant complete details of the qualification and experience requested under Part-II. Some additional information on Project may be seen at Annex

- Interested consulting firm(s)/ Joint Venture(s) must provide information indicating that they are qualified to perform above services (e.g. descriptions of similar assignments, value of previous assignments, experience under similar conditions, availability of appropriate professionals etc.).

- In accordance with World Bank Guidelines, an association of consultants can take either be in the form of joint venture (JV) or a subcontract (sub-consultancy). Therefore, the consultant submitting their Expression of Interest in association should clearly mention whether their association is a Joint Venture or Sub-consultancy. Moreover under JV, each partner has to be reasonably qualified to take over the responsibilities and role of any of the partners in case one of them fails to perform or withdraws. Thus, the experience of all the firms in the JV will be considered for evaluation. In case of Sub-consultancy association, the Lead Firm must be clearly mentioned in the EOI.

- A Consulting Firm/Joint Ventures will be selected in accordance with the Qualification and Cost Based Selection (QCBS) method set out in the WB Procurement Regulations for IPF Borrowers (Procurement in Investment Project Financing, Goods, Works, Non-Consulting and Consulting Services - Fourth Edition, November 2020).

- It is expected that the interested firm(s)/ joint venture(s) will have expertise in the areas of;(details at Annex-A)

- If the EOI consists of more than one volume, the applicant must clearly number the volumes constituting the EOI and provide an indexed table of contents for each volume. All documents should be securely bound.

- Guidelines for Selection and Employment of Consultants by World Bank Borrowers, can be accessed at the website: www.worldbank.org/procure.

PART-II

(ESSENTIAL INFORMATION REQUIRED TO BE PROVIDED BY CONSULTANT)

- Name, address, Phone, Fax and E-mail address along with postal and telegraphic address for the head office, branch offices and contact personnel.

- Certificate of Registration of the firm as Legal Entity

- Firm(s)/ joint venture(s) name, address, copy of the Registration Certificate with relevant professional bodies of the concerned Government, supported by latest/ updated renewal, Country of Operations (if the firm is registered and operating in several countries). Memorandum/ Article of Association/ Partnership Deed or Joint Venture Agreement (if applicable) etc;

- Names and short CVs of principals, proprietor, managing director, partners and directors, including their individual copy of the Registration Certificate with relevant professional bodies along with updated renewal.

- Details of the technical personnel available with the firm either as permanent staff or retainer consultants with their qualifications and expertise, briefly.

- Sound financial position with documentary evidence in the form of last three years audited financial accounts’ statement of the firm/joint venture members.

- National Tax Number of the firm/joint venture/consortium members (for national firms)

- Data Sheets of relevant (similar and specific experiences) assignments/works, duly substantiated, by the firm(s)/ Joint Venture(s) members either completed or in progress, with the following details.

  - Name of the Project

  - Cost of the Project

  - Name and address of the Client

  - If case of association of Consultant(s), the type of association i.e. either JV or sub-consultants be mentioned clearly along with names and address of all the partners.

  - Consultancy services rendered along with the Start & Completion Date.

  - A firm, which was a partner in a previous joint venture(s), should furnish a statement providing details of work, component of works performed individually and its over-all share (percentage) in the works performed by the joint venture.

- Any additional documents to support relevant experience of firm(s)/ Joint Venture(s);

- List and status of litigation/arbitration by the firm or any member of the joint venture(s) against a client, if any.

- Affidavit from all the participating partners of the association confirming that: (a) applicant firm(s)/ joint venture(s) have never been blacklisted by any International, Government/ Semi Government Organization and (b) All the information provided by the applicant firm(s)/ joint venture(s) is correct.

Any further information/clarification may be sought from;

Project Director

Housing Reconstruction Unit (HRU)-IFRAP

H. No 57-A Chaman Housing Society Airport Road Quetta

Ph. No-0812081372

Annex-A:

Background:

The 2022 floods in Pakistan, caused by heavy monsoon rains from June to September, significantly impacted the Sindh and Balochistan provinces, affecting 33 million people and destroying over 13,000 kilometers of roads. Infrastructure damages included 2.2 million homes and approximately 9.4 million acres of agricultural land, coupled with the loss of about 1.2 million livestock, severely impacted rural livelihoods. Market access limitations and supply chain disruptions led to a spike in food prices and severe food shortages, with inflation rising above 50 percent. The destruction of critical infrastructure also compromised access to education and healthcare, affecting long-term human capital development. The national poverty rate is projected to increase by up to 4 percentage points, potentially pushing an additional 9 million people into poverty. The Post-Disaster Needs Assessment (PDNA) estimates rehabilitation and reconstruction needs at US$16.3 billion, excluding further investments to bolster resilience against future disasters.

The 2022 floods have significantly affected Balochistan, exacerbating the socioeconomic challenges and increasing the multidimensional poverty rate from 70.2% to 81.1%. Agriculture, which represents 52% of the provincial GDP and employs 67% of the workforce, suffered the most. The province lost over 500,000 livestock—63% of the national total—resulting in production losses of PKR 79,619 million. This has severely impacted the livelihoods of 70% of households that depend on livestock. Crop failures during the Kharif season further compromised food security and livelihoods. Since the floods, commodity prices have spiked, leading to the highest rate of food insecurity in the country at 23.4% in Balochistan.

The province also sustained extensive damage to its infrastructure, including the destruction of 305 primary health facilities and damage to another 282, disrupting essential health services. As a result, 59% of the population now lacks adequate access to health care. Additionally, about 2,000 classrooms were damaged across 515 villages, with recovery costs exceeding PKR 24.4 million. Infrastructure damages have effectively isolated most of the province, with 2,222 km of roads and 43 bridges damaged, severely restricting access to healthcare, markets, and other vital services.

The floods also damaged over 190,000 housing units, including nearly 69,000 units destroyed and more than 120,000 partially damaged. Disruptions in cellular networks have further hindered economic activities. Additionally, 456 flood protection and irrigation schemes have been either partially damaged or destroyed, compounding the region's challenges.

# 2. Project Overview

## The PDNA and the Resilient Recovery, Rehabilitation, and Reconstruction Framework (4RF) suggest that cross-sector recovery requires both short- and medium-term reconstruction and rehabilitation as well as long-term critical reforms to address resilience and to build back better. Against this backdrop, the Government of Pakistan (GoP) requested the World Bank to urgently support the immediate needs of Balochistan for flood recovery and reconstruction in core socioeconomic sectors to help restore livelihoods and essential services, including housing, WASH, transport, agriculture, and irrigation, while building a foundation for long-term flood resilience through strengthening institutions and information (including hydro met and early warning capacities) through the Integrated Flood Resilience And Adaptation Project (IFRAP).

# 3.  Objectives of the Consultancy

The primary objective of this engagement is to implement HRU’s (the Client) communication strategy to reach out to key stakeholders especially the beneficiaries, as well as enhance the visibility and communication efforts of HRU-IFRAP through effective media management and communication strategies. Specifically, the following objectives are outlined:

### Key Message Development:

  - Develop and deliver clear, concise, and compelling messages that effectively inform beneficiaries and ensure their feedback is properly captured and documented.

  - Craft and convey clear, compelling messages that effectively highlight the Client’s mission, achievements, and current initiatives.

  - Ensure that these messages are culturally appropriate considering our target audience. Creation of High-Quality communications material:

  - HRU-IFRAP branding and designing

  - Design and produce visual content such as infographics, posters, banners, and short videos on project activities to showcase the impact, including testimonials of the beneficiaries and project people where required. .

### Establishing Media Relations:

  - Build and maintain strong relationships with key local, national, and international media outlets to ensure consistent coverage of HRU-IFRAP activities.

  - Ensure that the organization’s work is well-represented across various media platforms, including print, digital, and broadcast.

### Planning National, Provincial, District Level Events

  - Develop plans, presentations and events at the national, provincial and district levels for HRU.

  - Ensure proper coverage of these events in national and local media (electronic/print).

### Comprehensive Media Strategy and Planning:

  - Execute  the HRU-IFRAP media strategy by developing a content calendar for regular updates, events, and campaigns.

  - Plan and execute media events, including press conferences, public awareness campaigns, and special outreach initiative in consonance with the HRU Communication Strategy.

### Communicating with the beneficiaries:

### To effectively communicate with our beneficiaries, we employ a variety of channels, including:

### Sermons from Mosques: Partnering with local religious leaders to deliver key messages and updates during Friday sermons, ensuring that information reaches a wide audience in the community.

### Information, Education, and Communication (IEC) Materials: Distributing pamphlets, posters, and brochures in multiple languages to accommodate the diverse linguistic landscape of Balochistan, ensuring that our messages are accessible to all.

### Community Meetings and Workshops: Organizing regular gatherings to engage directly with beneficiaries, address their concerns, and provide updates on ongoing and upcoming projects.

### Radio and Television Broadcasts: Utilizing local media outlets to broadcast information about HRU-IFRAP’s initiatives, reaching both urban and rural audiences.

### Social Media Platforms: Engaging with the public through Facebook, Twitter, and Instagram, sharing stories of impact, project milestones, and important announcements.

### Mobile SMS and WhatsApp Campaigns: Sending timely messages to beneficiaries to provide updates, reminders, and important information about the housing reconstruction efforts.

### Broadening Outreach:

  - Work to ensure that HRU-IFRAP’s initiatives receive extensive media coverage, engaging diverse stakeholders, including government entities, donor organizations, and the general public, both within Balochistan and beyond.

# 4. Scope of Work

The selected media and communication firm will undertake the following tasks:

#### A. Strategic Communication

- Develop the detailed and comprehensive communication plan that aligns with HRU-IFRAP’s mission, objectives, communication strategy, and timeline.

- Identify specific target audiences and tailor key messages that resonate culturally and socially.

- Craft compelling messages, press releases, op-eds, blog posts, and news articles to emphasize project milestones and successes.

- Provide expert guidance on launching advocacy campaigns to raise awareness among policymakers, donors, and community stakeholders.

#### B. Content Creation

- Design visually impactful materials, including infographics, posters, banners, brochures, and booklets, to effectively communicate HRU-IFRAP’s work.

- Produce high-quality video content, such as:

  - Short promotional videos highlighting project goals.

  - Comprehensive documentaries showcasing HRU-IFRAP’s progress and community impact.

  - Event-focused videos capturing key moments and testimonials.

- Develop consistent branding guidelines to ensure all materials reflect HRU-IFRAP’s identity.

- Incorporate storytelling techniques to engage and inspire various audiences.

#### C. Media Relations and Outreach

- Build and maintain strong relationships with local, national, and international media outlets to ensure consistent coverage of HRU-IFRAP’s initiatives.

- Coordinate media events, including press briefings, interviews, and on-site visits to project locations.

- Develop and distribute media kits containing essential project information, statistics, and case studies to journalists and influencers.

- Align all media activities with HRU-IFRAP’s broader communication objectives to maximize reach and impact.

#### D. Event Coverage

- Provide comprehensive media coverage for HRU-IFRAP events, such as:

  - Press conferences to announce key developments.

  - Community engagement sessions to showcase grassroots impact.

  - Awareness campaigns to highlight reconstruction efforts.

- Capture high-resolution photographs and videos from all events for dissemination on media platforms.

- Organize and manage live streaming of events on multiple platforms to increase accessibility and engagement.

#### E. Digital Engagement

- Manage and regularly update HRU-IFRAP’s online presence, including its website and social media platforms (Facebook, Twitter, YouTube, LinkedIn, etc.).

- Create and publish engaging content, including:

  - Real-time updates on project activities.

  - Visuals and videos to illustrate progress and impact.

  - Interactive posts to foster audience engagement.

- Monitor digital engagement metrics (e.g., website traffic, social media interactions) to evaluate performance.

- Implement SEO strategies to enhance the visibility and searchability of HRU-IFRAP’s online content.

#### F. Reporting and Documentation

- Develop detailed monthly media coverage reports, highlighting key achievements, media interactions, and engagement statistics.

- Document project success stories through:

  - Written narratives that showcase the human impact of HRU-IFRAP’s initiatives.

  - Photo essays and video testimonials from beneficiaries.

- Archive all raw and edited media files with comprehensive metadata for easy retrieval and future use.

- Prepare comprehensive evaluation reports on media campaigns, detailing:

  - The effectiveness of various outreach strategies.

  - Lessons learned and recommendations for future initiatives.

# 5. Deliverables

The firm is required to deliver the following outputs:

| Deliverables | Details | Timeline |
| --- | --- | --- |
| Media Strategy | Review and improve the Communication and Media Strategy Document Developed by HRU outlining tools and methods to maximize coverage and engagement. Clear strategies for local, national, and international media engagement. | Within the first 2 weeks of engagement |
| Content Calendar | A detailed content calendar outlining planned activities, including media campaigns and press releases. Scheduling of media events, awareness campaigns, and outreach initiatives. | By the end of Week 3 |
| Media Materials | High-quality infographics, posters, banners, videos, and documentaries promoting HRU-IFRAP’s achievements. Regular & daily Content to be developed reflecting new progress and developments of HRU for social media, Website and Print/Electronic Media. | Delivered monthly; updates as needed |
| Media Coverage Reports | Monthly reports tracking key engagement metrics (e.g., articles published, social media interactions). Analysis of media coverage to assess the effectiveness of communication efforts. | Delivered by the 5th of each month |
| Campaign Evaluation | Evaluation reports assessing the impact of media campaigns and recommending improvements. | Quarterly basis (end of every 3 months) |
| Documentaries | Develop scripts and produce at least one documentary per month on HRU-IFRAP’s progress and social impacts. Showcase the documentaries across all relevant platforms. | Delivered by the end of each month |
| Advertisements | Create and broadcast advertisements on leading TV channels during prime time for effective coverage. | As required; initial plans finalized within 6 weeks |
| Monitoring and Evaluation | Monitor media campaigns and submit detailed reports on a monthly, quarterly, and annual basis. | Ongoing; monthly, quarterly, and annual submission |
| Event Coverage Materials | High-quality photo and video coverage of events, delivered within 12 hours for timely dissemination. | Delivered within 12 hours of event conclusion |
| Press Releases | Develop press releases for major events and ensure emergency/crisis media management when required. | Within 24 hours of an event or as required |

# 6. Team Composition and Qualifications

The firm must have a team of qualified professionals, including:

| Position | Required Staff | Qualifications | Responsibilities |
| --- | --- | --- | --- |
| Key Staff |  |  |  |
| Team Leader | 1 | - Masters in communications or social sciences (at least sixteen years of education) from a reputable international or HEC recognized national university - 10 plus years demonstrated experience of managing development communications of multi-sectoral projects. - Expertise in the design and implementation of communications, community mobilization and outreach strategies and public information campaigns - Strong leadership and project management skills with track-record of working with interdisciplinary project teams and managing communications and design professionals. - Excellent verbal and written communication skills in English and Urdu. Skills in local languages of Balochistan will be accorded weightage - Proficiency with Microsoft Office (Excel, PowerPoint, Word) with excellent presentation skills | - Oversee overall project planning, execution, and monitoring. - Ensure alignment with HRU-IFRAP objectives and timelines. - Coordinate across teams and stakeholders. - Review and approve deliverables. - Prepare detailed progress and performance reports for stakeholders. |
| Design & Creative Coordinator | 1 | - Masters in communications or social sciences (at least sixteen years of education) from a reputable international or HEC recognized national university. - 5 years demonstrated experience of working with reputable creative and advertising agencies. - Expertise in design and implementation of creative strategies, creative concepts, key messages, visual branding, and communications campaigns - Track record of developing and customizing creative campaigns for specialized target audiences, particularly less literate and marginalized groups in various formats - Excellent verbal and written communication skills with impeccable copy-editing expertise in both English and Urdu. Fluency in regional languages preferable - Proficiency with Microsoft Office (Excel, PowerPoint, Word) and basic knowledge of Adobe design suites | - Creative Strategy & Visual Branding: Lead the design and implementation of visual communication strategies - Develop creative concepts, key messages, and branding elements aligned with HRU-IFRAP’s goals - Customize creative campaigns for diverse and marginalized audiences, especially less literate groups - Content Supervision & Messaging: Oversee visual content creation including infographics, posters, and banners - Ensure all designs reflect consistent branding and cultural relevance - Collaborate with writers and multimedia teams to maintain message clarity and resonance - Coordination & Review: Serve as a liaison between design professionals and the broader communication team - Maintain creative oversight across digital, print, and broadcast formats - Review and refine materials for accuracy, aesthetics, and strategic impact - Communication Proficiency: Demonstrate strong copy-editing skills in English and Urdu - Fluency in Balochi or other local languages is preferred to improve outreach impact - Deliver presentations and pitch creative ideas using tools like PowerPoint and Microsoft Office |
| Content Writers | 2 | - Master’s degree in Communications, Journalism, or related field. - Minimum 5 years of experience in writing for diverse media platforms. - | - Develop press releases, blog posts, articles, and op-eds. - Tailor content for various media platforms. - Ensure all written content aligns with HRU-IFRAP’s messaging strategy. - Crisis communication Content Development |
| Non-Key Staff |  |  |  |
| Graphic Designers | 2 | - Bachelor’s or Master’s degree in Graphic Design or related field. - Minimum 5 years of experience in creating designs for print and digital platforms. - Proficiency in design software, including Adobe Creative Suite or similar. | - Create visual content, including infographics, posters, and banners. - Maintain consistency with branding guidelines. - Design engaging visuals for social media platforms. |
| Video Editors | 2 | - Bachelor’s or Master’s degree in Film Production or related field. - Expertise in video editing software such as Adobe Premiere Pro or Final Cut Pro or similar. - Minimum 5 years of experience in editing promotional videos and documentaries. | - Edit high-quality videos and documentaries. - Incorporate color grading, audio mixing, and subtitles. - Ensure timely delivery of video content for campaigns and events. |
| Documentary Makers | 1 | - Bachelor’s or Master’s degree in Film Production, Journalism, or related field. - Proven expertise in documentary filmmaking with a strong portfolio. - Experience in using drones and advanced filming equipment. | - Direct and produce impactful documentaries. - Manage storytelling elements to engage and inspire audiences. - Oversee all stages of documentary production from scripting to editing. |
| SEO and Web Developers | 1 | - Bachelor’s or Master’s degree in Computer Science, IT, or related field. - Proficiency in web development tools and SEO practices. - Proven experience in managing online content. | - Manage and update HRU-IFRAP’s website. - Optimize digital content for search engines. - Analyze website metrics and implement improvements. |
| Social Media Experts | 1 | - Bachelor’s or Master’s degree in Marketing, Communications, or related field. - Minimum 5 years of experience in social media management. - Familiarity with paid ad campaigns and engagement analytics. | - Develop and execute social media campaigns. - Manage daily social media activities. - Analyze performance metrics to improve engagement. |
| Photographers | 2 | - Bachelor’s or Master’s degree in Fine Arts or Photography. - Minimum 5 years of experience in project/event photography. - Expertise in photo editing software like Adobe Photoshop. | - Capture high-quality images for campaigns, events, and progress updates. - Provide edited visuals for media and communication materials. - Ensure quick turnaround for urgent content needs. |

# 7. Eligibility Criteria for Firm Selection

Firms must meet the following criteria to be considered for selection:

- Experience:

  - Minimum of 10 years of experience in media and communication. Experience in disaster recovery, resilience, or humanitarian projects will be accorded due weightage

  - At least three successfully implemented media campaigns within the last 5 years of comparable scale and complexity as defined in TOR.

  - Demonstrable expertise in developing and implementing multi-platform communication plans.

- Technical Expertise:

  - The firm must possess:

    - Expertise in producing video documentaries of minimum 15 minutes length, aligned with international standards.

    - Proven ability to design and execute visual storytelling campaigns with measurable audience engagement metrics.

- Media Linkages:

  - Evidence of established partnerships with leading national and international media outlets (e.g., CNN, BBC, Dawn, Geo News).

  - Proven track record of securing media placements for development-sector initiatives.

# 8. Duration of the Project

The selected Media and Communication Firm will be engaged for a period up to June 2027. needs.

# 9.  Selection Method:

A consultant will be selected in accordance with Quality and Cost-based Selection World Bank’s Guidelines: Selection and Employment of Consultants by World Bank Borrowers (Nov 2020).

# 10. No OBJECTION CERTIFICATE:

Obtaining NOCS from Provincial Government, local administration, and relevant local security agencies for carrying project activities in target districts (as per phased approach) can be crucial for timely initiation of project activities. Pertaining to this, Client will provide facilitation to the Firm in terms of carrying out official correspondence with the concerned authorities. However timely provision of required information to the concerned authorities as well as follow-ups for expediting the process of NOC to get it as early as possible will be the final responsibility of the firm.